AMPM BUILDING SERVICES LIMITED

Launch Readiness Plan

Mobilisation to go-live

Go-live: 1 July 2026

A trading subsidiary of AMPM Group Limited

Version 1.0   |   June 2026   |   Strictly Confidential

# 1.  Purpose and Critical Path

This plan tracks everything required to launch AMPM Building Services Limited cleanly on 1 July 2026. It complements the Launch Business Plan (the why and the financials) with the operational how — workstreams, owners, statuses and the decisions outstanding.

Headline. Corporate set-up, bank account and Xero are done. Commercial momentum is real — Dan has clients willing to trade. The critical path now runs through HR (SafeHR), the Integrated Management System, insurance, the inter-company people agreements and brand, all of which must land before 1 July.

Three things gate a clean launch and need a decision this week: the HR system go-live, the inter-company arrangements for seconded staff, and the insurance route. These are covered in Section 3.

# 2.  Mobilisation Tracker

| Workstream | Action / open question | Owner | Status | Target |
| --- | --- | --- | --- | --- |
| Corporate | Company incorporated; wholly owned by AMPM Group; structure set. | Jamie | Done | Complete |
| Banking | Trading bank account opened. | Jamie | Done | Complete |
| Finance — Xero | Separate Xero entity set up on the Group account. | Jamie | Done | Complete |
| HR — SafeHR | Stand up Building Services on SafeHR (contracts, holiday, H&S) before any staff move across. | TBC | To do | By 23 Jun |
| Project systems — Procore | Decide and confirm: extend Group Procore to BS; seat/licensing basis. | Dan / Becca Lee | Decision | By 20 Jun |
| Asset systems — Uptick | Second company in existing instance vs separate subscription. Recommendation: defer until PM contracts land. | Becca Lee | Decision | Defer |
| IMS | Clone Gemini's Integrated Management System and rebrand for BS; common standards across the Group. | Becca Lee | In progress | By 27 Jun |
| Insurance | Confirm route with broker: Gemini umbrella for Phase 1; own EL/PL/PI before Phase 2. | Luke / broker | In progress | Umbrella by 30 Jun |
| People — secondments | Inter-company recharge/secondment agreements: Steve Lee (projects), Joe Isaac, Jill Wilson (1 day/wk). | Jamie / Luke | To do | By 30 Jun |
| Accreditations | Submit NICEIC/Gas Safe and CHAS applications; Constructionline to follow. | Becca Lee | In progress | Submit by 20 Jun |
| Brand / stationery | Logos, letterheads, email signatures, stationery; consistent Group identity. | Jamie | In progress | By 27 Jun |
| Domain / web | ampmbuilding.services — resolve SSL/privacy error; site live for launch. | Jamie | In progress | By 30 Jun |
| Commercial | Convert Dan's client conversations to first enquiry; identify first Gemini sub-contract package. | Dan | In progress | From 1 Jul |

# 3.  Decisions Needed Now

## 3.1  HR system — SafeHR go-live

Decision: confirm SafeHR is configured for Building Services before anyone transfers in. Recommendation: treat as the top pre-launch priority. No one — Steve Lee included — should move across without contracts, holiday and H&S records in place. Owner and date to be assigned this week.

## 3.2  Inter-company people arrangements

Decision: how Steve Lee, Joe Isaac and Jill Wilson are engaged. Recommendation: a short secondment/recharge agreement for each — Gemini invoices Building Services for their time at cost-plus. Steve Lee's move is a contractual variation or internal transfer by agreement (an intra-group move; full TUPE machinery is unlikely to be needed, but document it). This keeps Building Services carrying its own cost and stops Gemini quietly subsidising the launch — the core de-risking principle.

## 3.3  Insurance route

Decision: confirm with the Group broker that Phase 1 (sub-contracting into Gemini) can run under Gemini's umbrella while the entity's own EL/PL/PI is placed, and the date the standalone cover binds. Recommendation: umbrella confirmed before 1 July; own cover bound before the first Phase-2 direct instruction.

## 3.4  Systems — Procore and Uptick

- Procore — extend group-wide. Consistency and golden-thread documentation favour one delivery platform. Confirm whether BS is a new company in the existing account or needs added seats (cost check).

- Uptick — defer. Planned-maintenance is not a Day-1 need. Do not buy a second subscription or complicate the instance until PM contracts land.

# 4.  People and Inter-Company Arrangements

| Person | Role in Building Services | Basis / action |
| --- | --- | --- |
| Jamie Dawson | Chair | Group role retained in NewCo. |
| Dan Small | Managing Director | Group role retained; leading client development. |
| Luke Finney | Commercial Director | Group role retained; owns insurance and commercial set-up. |
| Steve Lee | Head of Projects (project delivery) | Move across from Gemini — document as transfer/variation; SafeHR record before start. |
| Joe Isaac | Commercial / delivery support (1 day/week) | Secondment + inter-company recharge from Gemini. |
| Jill Wilson | Commercial / delivery support (1 day/week) | Secondment + inter-company recharge from Gemini. |
| Becca Lee | Compliance & systems (Gemini) | Supporting Uptick/IMS/accreditation set-up; recharge for time spent. |

Why this matters. Every pound of Gemini time spent on Building Services must be recharged. Without it, Building Services looks artificially profitable and Gemini absorbs a hidden cost — the opposite of what this structure is for.

# 5.  Systems Setup

| System | Status | Action |
| --- | --- | --- |
| Xero | Done | Separate entity live on the Group account ahead of first invoice. |
| SafeHR | To do | Configure BS instance: employment contracts, holiday, absence, H&S records. Live before staff transfer. |
| Procore | Decision | Extend Group platform to BS; confirm seat/licensing basis; set up first project. |
| IMS | In progress | Clone Gemini IMS; rebrand for BS; issue controlled documents; align to ISO 9001/14001/45001 for future certification. |
| Uptick | Decision | Defer. Revisit when planned-maintenance contracts are secured. |
| AMPM Live | In progress | Onboard BS clients to the Group portal at launch. |

# 6.  Insurance and Compliance Checklist

## 6.1  Insurance

- Employers' Liability — statutory £5m minimum; £10m recommended.

- Public Liability — £5m minimum; £10m for Tier-1 supply-chain.

- Professional Indemnity — £1–2m for design-and-build / specification work.

- Contract Works / All-Risks — required for most main-contractor appointments.

- Plant & Equipment — if plant is owned rather than hired.

Sequence: Gemini umbrella covers Phase 1; entity's own cover binds before Phase 2. Confirm both with the broker before 1 July.

## 6.2  Accreditation pipeline

- Month 1–3: NICEIC/NAPIT (electrical), Gas Safe, CHAS/SafeContractor.

- Month 2–4: Constructionline Gold for PQQ standard.

- Month 3–6: FMB / trade schemes; ISO alignment via the cloned IMS.

## 6.3  Brand and stationery

- Logo and visual identity consistent with the AMPM Group family.

- Letterheads, email signatures, business cards, document templates (tender, RAMS, O&M).

- Resolve the ampmbuilding.services SSL/privacy-error and confirm the site is live for launch.

# 7.  Pre-Launch Critical Path

Roughly three weeks to go-live. The sequence below puts the gating items first.

| Week | Focus | Gate |
| --- | --- | --- |
| Wk of 9 Jun | Assign SafeHR owner and start configuration; engage broker on umbrella + own-cover; draft inter-company secondment/recharge agreements; submit NICEIC/Gas Safe/CHAS; start IMS clone; confirm Procore extension; finalise logo. | Owners assigned; applications in. |
| Wk of 16 Jun | Populate SafeHR; issue rebranded IMS documents; confirm Gemini umbrella in writing; identify first Gemini sub-contract package; begin supply-chain qualification; produce letterheads and templates. | HR + IMS substantially ready. |
| Wk of 23 Jun | Execute secondment/recharge agreements; dry-run first invoice in Xero; finalise website/SSL and email signatures; board readiness review and sign-off. | Board sign-off; launch-ready. |
| 1 July | Go-live. Appoint to first package; Steve Lee in post; first Phase-1 revenue invoiced. | Trading. |

AMPM Building Services Limited  ·  Launch Readiness Plan  ·  v1.0 June 2026  ·  Strictly Confidential